## Sheet1
Idea Timeline | Week | Channel (Email, LinkedIn, Cold Calling, etc.) | ABM Activity | Description
Positioning and Asset Building | Week 1 | Demo of Technology | Feature Industry experts and preview their session insights. | Showcase the platform with industry experts and highlight key session insights
|  | audience mapping and outreach |  | Identify target audience segments and plan multi-channel outreach
|  | Finalize email template |  | Create and approve email template for the campaign
| Week 2 | Landing page content + design | Prep for ABM Campaign assets; landing page offering for target audience | Prepare ABM campaign assets for target accounts
Design landing page offering tailored to the audience
| Week 3 | Account Mapping (10 Top Picks) 10 priority accounts, divided into two phases of 5 each | Account Mapping & Landing Page (Content + Design) 10 priority accounts in 2 phases of 5 each | Identify 10 high-value “Big Bet” accounts and divide them into two phases of 5 each for focused outreach
|  | Landing Page (Content+Design) |  | Develop landing page content and design tailored to engage these priority accounts and support ABM campaign goals
Account Research & Messaging Development | Week 4 | Conduct deep research on accounts (firmographics, technographics, buying triggers) Craft precision email and LinkedIn messaging tailored to each persona Validate messaging with internal stakeholders and market context | Conduct deep research on accounts (firmographics, technographics, buying triggers), craft precision email and LinkedIn messaging tailored to each persona, and validate with internal stakeholders and market context | Conduct deep research on priority accounts, including firmographics, technographics, and buying triggers to inform outreach strategy
Craft personalized email and LinkedIn messaging for each persona and validate it with internal stakeholders for accuracy and relevance
Phase 1 Execution – Email & LinkedIn | Week 5 | Email + LinkedIn Post | Execution of 1 Pass by Email Execute LinkedIn Post 1 | Execute the first pass of personalized email outreach to target accounts
Publish the first LinkedIn post to engage priority accounts and support the campaign
| Week 6 | Email + Linkedin Post + Linkedin In-Mails + Cold Calling | Execution of 2nd Pass by Email. Execution of the 1st & 2nd pass of InMails to the top hot leads, each from Email 1 and 2. Reach out to warm leads via phone, WhatsApp, and a personalized LinkedIn connection. Execute LinkedIn Post 2 | Follow up on initial email outreach with a second pass and send targeted LinkedIn InMails to hot leads to deepen engagement and drive responses
Reach out to warm leads through phone, WhatsApp, and personalized LinkedIn connections while reinforcing campaign messaging with a second LinkedIn post
| Week 7 | Email + LinkedIn Post+ Cold Calling | Execution of 3rd Pass by Email Reach out to the warm leads via call, WhatsApp, and personalized LinkedIn connection. Execute LinkedIn Post 3 | Send the third pass of email outreach to continue nurturing engagement and follow up on previous interactions
Connect with warm leads through calls, WhatsApp, and personalized LinkedIn messages while reinforcing campaign messaging with a third LinkedIn post
| Week 8 | Email + Linkedin Post + Linkedin In-Mails+ Cold Calling | Execution of the 4th Last Pass by Email. Execution of the 3rd & 4th pass of InMails to the hot leads, each from Email 3 & 4. Reach out to warm leads via phone, WhatsApp, and a personalized LinkedIn connection. Execute LinkedIn Post 4 | Send the fourth and final pass of email outreach and targeted LinkedIn InMails to hot leads from previous emails to maximize conversions
Engage warm leads through phone, WhatsApp, and personalized LinkedIn connections while reinforcing messaging with the fourth LinkedIn post
Phase 2 Execution – Email & LinkedIn | Week 9 | Email + LinkedIn Post | Execution of 1 Pass by Email Execute LinkedIn Post 1 | Execute the first pass of personalized email outreach to target accounts
Publish the first LinkedIn post to engage priority accounts and support the campaign
| Week 10 | Email + Linkedin Post + Linkedin In-Mails + Cold Calling | Execution of 2nd Pass by Email. Execution of the 1st & 2nd pass of InMails to the top hot leads, each from Email 1 and 2. Reach out to warm leads via phone, WhatsApp, and a personalized LinkedIn connection. Execute LinkedIn Post 2 | Follow up on initial email outreach with a second pass and send targeted LinkedIn InMails to hot leads to deepen engagement and drive responses Reach out to warm leads through phone, WhatsApp, and personalized LinkedIn connections while reinforcing campaign messaging with a second LinkedIn post
| Week 11 | Email + LinkedIn Post+ Cold Calling | xecution of 3rd Pass by Email Reach out to the warm leads via call, WhatsApp, and personalized LinkedIn connection. Execute LinkedIn Post 3 | Send the third pass of email outreach to continue nurturing engagement and follow up on previous interactions Connect with warm leads through calls, WhatsApp, and personalized LinkedIn messages while reinforcing campaign messaging with a third LinkedIn post
| Week 12 | Email + Linkedin Post + Linkedin In-Mails+ Cold Calling | Execution of the 4th Last Pass by Email. Execution of the 3rd & 4th pass of InMails to the hot leads, each from Email 3 & 4. Reach out to warm leads via phone, WhatsApp, and a personalized LinkedIn connection. Execute LinkedIn Post 4 | Send the fourth and final pass of email outreach and targeted LinkedIn InMails to hot leads from previous emails to maximize conversions Engage warm leads through phone, WhatsApp, and personalized LinkedIn connections while reinforcing messaging with the fourth LinkedIn post