## Webinar Template
Idea Timeline | Week | Channel (Email, LinkedIn, Cold Calling, etc.) | ABM Activity | Description
Strategy and Positioning | Week 1 | Finalize webinar topic | Feature Industry experts and preview their session insights. | Finalize webinar topic and agenda
|  | Webinar audience mapping and outreach |  | Spotlight Guest speakers
|  | Finalize email template |  | Finalize email template for webinar
| Week 2 | Landing page content + design | Prep for ABM Campaign assets; landing page offering webinar for target audience | Require 3 weeks to prepare ABM campaign assets, including messaging scripts, landing page, stakeholder mapping, and Mailchimp email template.
Prepare content for the Webinar, including the landing page, with suggested taglines, layout, and CTA.
| Week 3 | Stakeholder Mapping | Prep for ABM Campaign assets; positioning target audience, messaging script, stakeholder mapping, Mailchimp email template | Assemble ICP lists for stakeholder mapping. Segment the audience into sets for each email. Note: Each set consists of approximately 200 audience memebers
|  | Email Messaging scripts |  | Prepare all 5-6 email touchpoints plus follow-ups for the webinar campaign.
|  | Linkedin Posts |  | Prepare 5 LinkedIn posts for the webinar campaign
|  | Landing Page (Content+Design) |  | Finalize landing page content and design
Demand Generation + Webinar Execution | Week 4 | Email + LinkedIn Post | Execution of 1st Pass by Email Execute LinkedIn Post 1 | Segment Email 1 into sets, consisting of approximately 200 audience members per set. Launch first outreach email 1 with ICP-align messaging.
Launch outreach email 1 Linkedin Post 1: Share a result, screenshot, client win, or system that worked (Attach industry experts' testimonials).
| Week 5 | Email + LinkedIn Post | Execution of 2nd Pass by Email Execute LinkedIn Post 2 | Segment Email 2 into sets, consisting of approximately 200 audience members per set. Execute Email 2: Follow-up on email 1 with ICP-align messaging.
Execute Email 2 (Follow-up on email 1) LinkedIn Post 2: Share a value-based framework post, focusing on key outcomes for the target audience and the value we offer Identify high-priority accounts for customized, high-value LinkedIn outreach for warm leads.
| Week 6 | Email + Linkedin Post + Linkedin In-Mails + Cold Calling | Execution of 3rd Pass by Email. Execution of the 1st & 2nd pass of InMails to the top hot leads, each from Email 1 and 2. Reach out to the warm leads via call, WhatsApp, and personalized LinkedIn connection. Execute LinkedIn Post 3 | Segment Email 3 into sets, consisting of approximately 200 audience members per set. Execute Email 3: Follow-up on email 2 with ICP-align messaging.
Execute Email 3 (Follow-up on email 2) LinkedIn Post 3: Use the Leadership messaging framework to offer a webinar campaign to the target audience. InMails to the hot leads from Email 1 and 2. Cold Calling: Short check-in for warm/unregistered leads
| Week 7 | Email + LinkedIn Post+ Cold Calling | Execution of 4th Pass by Email Reach out to the warm leads via call, WhatsApp, and personalized LinkedIn connection. Execute LinkedIn Post 4 | Segment Email 4 into sets, consisting of approximately 200 audience members per set. Execute Email 4: Follow-up on email 3 with ICP-align messaging.
Execute Email 4 (Follow-up on email 3). LinkedIn Post 4: Problem/Solution focus for the target audience, pitching webinar to the target audience. Identify high-priority accounts for customized, high-value LinkedIn outreach for warm leads. Cold Calling: Short check-in for warm/unregistered leads
| Week 8 | Email + Linkedin Post + Linkedin In-Mails+ Cold Calling | Execution of 5th Pass by Email. Execution of the 3rd & 4th pass of InMails to the hot leads, each from Email 3 & 4. Reach out to the warm leads via call, WhatsApp, and personalized LinkedIn connection. Execute LinkedIn Post 5 | Segment Email 5 into sets, consisting of approximately 200 audience members per set. Execute Email 5: Follow-up on email 4 with ICP-align messaging.
Execute Email 5 (Follow-up on email 4) LinkedIn Post 5: Focus on maximizing CTA towards the webinar campaign for the target audience InMails to the hot leads from Email 3 and 4 Cold Calling: Short check-in for warm/unregistered leads
Post Webinar LinkedIn + Email Campaign
Conversion and Insights | Week 9 | Follow-up Email | Follow-up 1 – Subject: Thanks for joining — Here’s what you missed | Reach out to warm leads who attended or registered for the Webinar through a follow-up email. Add Post Webinar Assets ( visual summary, infographics, short cuts).
Direct towards the post-webinar page showcasing all assets (reels, highlights, visual summary)
| Week 10 | Follow-up LinkedIn Post + Cold Calling + Social Media Snippets | Follow up on post-webinar LinkedIn Post 1 "Share webinar recap" Start reaching out to warm leads and attendees via call and WhatsApp channel | Attach all LinkedIn assets, i.e, reels, short videos, highlights Attach book strategic call link
| Week 11 | Follow-up Email | Follow-up 2 – Subject: Continuing the Conversation | Direct towards the post-webinar page showcasing all assets (reels, highlights, visual summary)